## Sheet1
TABLE 5.1 - CONSERVATION ACTION IMPLEMENTATION SCHEDULE - DRAFT
2014-10-20
Cost Estimates ($1,000)
|  |  | Task |  |  |  |  | Total
| Task | Task | Duration | Lead | Task | Funding | Funding | Estimated
Priority | No. | Description | (years) | Agency | Status | Source | Status | Cost | 2015 | 2016 | 2017 | 2018 | 2019
GOAL 1. PROTECT, MONITOR AND ENHANCE KEY KRRT POPULATIONS
Objective 1.1. Periodically (5-10 year intervals) monitor wild KRRT populations (segment 5).
1 | 1.1a | Periodically (5-10 years intervals) collect tissue samples from identified "pure" and slightly introgresed KRRT populations (Segment 5). | 1 | CDFW NGO | on going | CDFW | Funded
1 | 1.1b | Periodically monitor trout population structure and numbers in waters where trout are removed for broodstock development (Segment 5). | 1 | CDFW | on going | CDFW | Funded
Objective 1.2. Continue to search for additional KRRT populations and collect tissue samples for genetic analysis from trout populations of interest.
2 | 1.2a | Determine if additional waters in the Kern basin should be sampled in an effort to identify additional KRRT populations (All Segments) | annual | CDFW | Not started | CDFW | unfunded
2 | 1.2b | Collect tissue samples from Picket Creek, and possibly other streams, for DNA analysis | annual | CDFW NGO | Not started | CDFW | unfunded
Objective 1.3. Identify Potential Locations for KRRT refuge streams | [8 empty] | 2015 | 2016 | 2017 | 2018 | 2019
2 | 1.3a | Develop criteria for selecting KRRT refuge sites (Segments 1-5) | 1 | CDFW, SEKI, INF, SNF | 2015 | CDFW, SEKI, INF, SNF | Funded |  | $
2 | 1.3b | Work Federal Agencies to identify suitable KRRT refuge stream locations. (Segments 1-5) | 1 | CDFW, SEKI, INF, SNF | 2016 | CDFW, SEKI, INF, SNF | Funded |  |  | $
2 | 1.3c | Refine criteria for determining what constitutes a fish barrier. (Segments 1-5) | 1 | CDFW | 2017 | CDFW | Funded |  |  |  | $
3 | 1.3d | Conduct barrier surveys to identify KRRT refuge water(s). (Segments 1-5) | 3 | CDFW | 2017 | CDFW | Funded |  |  |  | $
Objective 1.4 – Remove existing fish populations from target refuge streams reaches(s) in preparation for KRRT introductions
2 | 1.4a | Conduct NEPA and CEQA, which includes public review and comment, on any proposed management actions that involves the elimination of existing fish populations and establishing KRRT population(s) (segments 1-5). | 3 | CDFW, SEKI, INF, SNF | not scheduled | CDFW, SEKI, INF, SNF | unfunded
3 | 1.4b | If a fish removal project were approved for selected stream(s) or stream segments, implement the removal program (segments 1-5). | 2 | CDFW | not scheduled | CDFW, SEKI, INF, SNF | unfunded
3 | 1.4c | Verify the target stream(s) are fishless following chemical treatments. (Segments 1-5) | 1 | CDFW | not scheduled | CDFW | unfunded
Objective 1.5 – Transplant RTKT from donor population(s) into refuge waters to establish two to three refuge populations. (Segments 1-5)
1 | 1.5a | Monitor population structure in donor KRRT populations before and after trout removal (Segments 5). | 2 | CDFW | initial phase completed | CDFW | ongoing
3 | 1.5b | Transplant KRRT from the pure donor population(s) into one to three refuge waters to establish viable KRRT populations. Segments 1-5 | 2 | CDFW | not approved | CDFW | not started
3 | 1.5c | Periodic (10-15 years cycle) genetic monitoring of refuge KRRT populations to ensure they reflect the genetic composition of the source population (segment 1-5). | 1 | CDFW | not approved | CDFW | not started
Objective 1.6. Evaluate the conservation value of trout populations prior to their removal for amphibian restoration in SEKI waters.
1 | 1.6a | Collect fin samples for genetic analysis if appropriate. | annual | SEKI | ongoing | SEKI | KRTF
1 | 1.6b | Conduct genetic analysis on selected trout populations slated for removal for ecosystem restoration. | annual | SEKI | ongoing | SEKI | KRTF
GOAL 2. PROTECT, ENHANCE AND MONITOR KEY RIPARIAN AND AQUATIC HABITATS
Objective 2.1. Monitor physical parameters at key locations to determine if significant changes are occurring. (All segments).
2 | 2.1a | Monitor physical parameters at key locations to determine if climate change is occurring locally and to what extent. Consider these parameters in adaptive management planning. | 1 | ?, SCE | ongoing
1 | 2.2a | Monitor sediment levels in the Kern River and key tributary streams to determine trends over time. (Applies to all segments, but primary segments 1 through 4). | 1 | CDFW, SCE | ongoing
1 | 2.2c | Include the monitoring and protection of riparian habitat when projects are implemented within the Kern River watershed | multiple | INF, SNF | ongoing?
Objective 2.2. Identify and Conduct habitat improvement and restoration projects in key Kern River watersheds. | [7 empty] | Total est cst
1 | 2.2a | Work with land owners/managers to reduce or mitigate management activities that might negatively impact KRRT populations and their habitats (all segments). | annual | INF, SNF, INF | ongoing? | INF, SNF
| 2.2b | Work with Agencies to prioritize habitat restoration projects if needed to expand range |  | INF, SNF, INF
1 | 2.2c | Conduct Physical Meadow restoration projects | annual | INF, SNF | ongoing | INF, SNF
2 | 2.2d | Monitoring of post restoration conditions for Osa, Last Chance and Long Meadow restoration projects. (Segment 4). | annual | INF, SNF | ongoing | INF, SNF
3 | 2.2e | Identify additional meadows and riparian locations for restoration projects. | annual | INF, SNF | planned | INF, SNF
GOAL 3. MANAGE FOR A SATISFACTORY WILD TROUT AND HATCHERY SUPPORTED TROUT FISHERY
Objective 3.1. – Monitor wild trout populations and angler success (Segments 3, 4 and 5). | [8 empty] | 2015 | 2016 | 2017 | 2018 | 2019
2 | 3.1a | Monitor the 4-mile long special angling regulation river reach upstream of Johnsondale Bridge every 5-10 years (Segment 3). | 1 | CDFW | ongoing | CDFW | funded |  | X
1 | 3.1b | Use angler box survey forms to evaluate trends in the fishery and angler success and satisfaction (Segments 3). | annual | CDFW | ongoing | CDFW | funded
1 | 3.1c | Monitor angler success and satisfaction in Segment 4 (Segment 4) | annual | CDFW | ongoing | CDFW | funded
1 | 3.1d | Monitor angler success and satisfaction in Segment 5 (Segment 5) | annual | CDFW | ongoing | CDFW | funded
2 | 3.1e | Establish 2 permanent electrofishing monitoring transects in Upper and Lower Peppermint Creek | 1 | CDFW | not started | CDFW | funded
Objective 3.2. Ensure Current Angling Regulations are Resulting in Satisfactory Wild Trout Fishery (Segments 3, 4, and 5).
1 | 3.2a | Review and make recommendations, if needed, to angling regulations upstream of Johnsondale Bridge to ensure they are resulting in a satisfactory wild trout fishery (Segments 3, 4 and 5). | 1 | CDFW | not started | CDFW | funded
1 | 3.2b | Use fish population and angler survey monitoring results to support proposed changes (if appropriate) to angling regulations (Segments 3, 4 &5). | 1 | CDFW |  |  | funded
1 | 3.2c. | Collect addition trout population information if needed (Segment 5) | 1 | CDFW | Not sure if necessary yet | CDFW | funded
Objective 3.3 – Provide anglers with a satisfactory hatchery supported trout fishery. (Segments 1, 2 and 4;
1 | 3.3a | Continue current hatchery non-native rainbow trout stocking program until native KRRT become available. (Segments 1, 2 and 4) | annual | CDFW | ongoing | CDFW | funded | ?
Objective 3.4. Initiate the Conversion of Kern River Planting Base to a Hatchery | [7 empty] | Total est cst | 2015 | 2016 | 2017 | 2018 | 2019
1 | 3.4a | Add a Fish and Wildlife Technician to the KRH staff | annual | CDFW | scheduled | CDFW | funded | 46
1 | 3.4b | Add one Seasonal Aid to the KRH staff | annual | CDFW | scheduled | CDFW | funded | 17
1 | 3.4c | Employee Overtime | annual | CDFW | scheduled | CDFW | funded | 10
2 | 3.4d | Electrical costs | annual | CDFW | scheduled | CDFW | funded | 20
2 | 3.4e | Fish Food | annual | CDFW | scheduled | CDFW | funded | 25
1 | 3.4f | General Expense | annual | CDFW | scheduled | CDFW | funded | 20
2 | 3.4g | Packstock Rental | 1 | CDFW | scheduled | CDFW | ? | ?
2 | 3.4h | Disinfecting foot baths | annual | CDFW | scheduled | CDFW | ? | ?
2 | 3.4i | Egg & Equipment Disinfection | annual | CDFW | scheduled | CDFW | ? | ?
1 | 3.4j | New Zealand mud snail monitoring | annual | CDFW | ongoing | CDFW | ? | ?
3 | 3.4k | Hatchery Interpretive Projects | annual | CDFW | scheduled | CDFW | ? | ?
3 | 3.4l | Use tags to identify individual KRRT | annual | CDFW | not scheduled | KRRT | unknown | ?
Objective 3.5. Fund Kern River Hatchery anticipated onetime costs | [7 empty] | Total est cst | 2015 | 2016 | 2017 | 2018 | 2019
1 | 3.5a | Replace Emergency Water evacuation pump | 1 | CDFW | scheduled | HIFF | funded | 25 | 25
1 | 3.5b | Liquid Oxygen Supplementation | 1 | CDFW | scheduled | HIFF | funded | 25 | 25
1 | 3.5c | Add a Leaf removal system | 1 | CDFW | scheduled | KRTF | unfunded | 120 | 120
2 | 3.5d | Settling Ponds, Influent and Effluent | 3 | CDFW | scheduled | HIFF | funded | 50 |  | 50
2 | 3.5e | Existing pond repairs and improvements | 3 | CDFW | scheduled | HIFF | funded | 325 |  | 325
2 | 3.5f | Design and Install Fish Screens | 3 | CDFW | scheduled | HIFF | funded | 10 |  | 10
1 | 3.5g | Drum micro filtration system | 1 | CDFW | scheduled | KRTF | funded | 50 | 50
1 | 3.5h | U.V. sterilization | 1 | CDFW | scheduled | KRTF | funded | 10 | 10
3 | 3.5i | Remodel three employee residences. | 2 | CDFW | unknown | HIFF | funded | 165
2 | 3.5j | Modify existing raceways to better replicate a natural stream environment | 2 | CDFW | scheduled | HIFF | funded | 25 |  | 25
? | 3.5k | Flow Meter in Siphon Pipe | 1 | CDFW | unknown | HIFF | funded | 5 | ???
3 | 3.5l | Replace existing Siphon pipe | 2 | CDFW | scheduled | unknown | unfunded | 1000 |  |  | 1000
3 | 3.5m | Replace roof on hatchery building | 1 | CDFW | scheduled | HIFF | funded | 10 |  |  | 10
3 | 3.5n | Quarantine Station at San Joaquin Hatchery | 2 | CDFW | scheduled | HIFF | funded | 50 |  |  | 50
3 | 3.5o | Construct Spawning Building and new fish-way | 2 | CDFW | scheduled | HIFF | unfunded | 250
2 | 3.5p | Water chiller | 1 | CDFW | scheduled | HIFF | unfunded | 250 |  | 250
1 | 3.5q | Collect 30-40 wild rainbow trout and bring them into KRH on a trial basis. | 1 | CDFW | scheduled
Objective 3.6 – Implement the Hatchery Genetics Management Plan (HGMP)
1 | 3.6a | Use the Genetics Management Plan to guide the collection of KRRT from selected Kern River Tributary Streams. | 3 | CDFW | ongoing
1 | 3.6b | Develop an MOU between CDFW and SEKI that would allow the removal of KRRT from Park waters. | 1 | CDFW | ongoing
2 | 3.6c | Collect KRRT population data from one or more of the four KRRT populations permitted by SEKI | 2 | CDFW SEKI | ongoing
1 | 3.6d | Ensure all gear used in the collection and monitoring of pure KRRT populations has been disinfected or is new to prevent the transmission of any diseases. | annual | CDFW | ongoing
1 | 3.6e | Coordinate with SEKI and SQF on numbers, size and locations for any removal of KRRT for broodstock (Segment 5) | 2 | CDFW SQF SEKI | ongoing
1 | 3.6f | Develop a KRRT Hatchery Broodstock Program. | annual | CDFW | ongoing
1 | 3.6g | Collect wild KRRT for broodstock according to HGMP | 2 | CDFW | ongoing
1 | 3.6h | CDFW pathologist to certify all wild trout being transferred to KRH | 2 | CDFW | ongoing
1 | 3.6i | Mark each KRRT with fin clips, VIE, pit tags or other marking techniques to identify source stream and year collected. | 2 | CDFW | scheduled
| 3.6j | Develop a KRRT Broodstock | annual | CDFW | scheduled
2 | 3.6k | Monitor the genetic diversity of the hatchery KRRT broodstock | 1 | CDFW | scheduled
3 | 3.6l | Monitor trout populations that are currently heavily introgressed, but are the subject of hatchery KRRT stocking | 1 | CDFW | scheduled
Objective 3.7 – Gradually replace the stocked non-native trout with hatchery reared KRRT
2 | 3.7a | Produce approximately 262,000 KRRT annually for stocking in the Kern River and area waters. (Segments 1-4). | annual | CDFW | not started
1 | 3.7b | Continue Trophy trout program using KRRT in segment 1 and Lake Isabella | annual | CDFW | ongoing
3 | 3.7c | Produce 50,000 catchable size KRRT to stock in Lake Isabella | annual | CDFW | not started
3 | 3.7d | Produce 12,000 catchable size KRRT to stock below Lake Isabella | annual | CDFW | not started
3 | 3.7e | Produce 50,000 catchable KRRT for waters planted from KRH, but outside the basin | annual | CDFW | not started
3 | 3.7f | Seek approval to introduce KRRT into tributary stream to Tulare Lake | 1 | CDFW SQF | not started | N/A | N/A | 0 |  | X
Objective 3.8 – Monitor KRRT contribution to the fishery in tributary streams and overall angler success.
2 | 3.8a | Evaluate the contribution to the fish population of stocked KRRT in tributary streams. | annual | CDFW | not started
2 | 3.8b | Monitor the harvest of planted rainbow trout (Segment 1, 2, 3 and 4) | annual | CDFW | not started
Objective 3.9. Develop an experimental pilot program for KRRT to determine if this can be a put-and-grow program.
3 | 3.9a | Evaluate the contribution of stocked fingerling and sub-catchable KRRT to the population to determine if a put-and-grow program is a useful management tool. | 4 | CDFW | 2018 | [6 empty] | $
Objective 3.10. Enforce angling regulations
1 | 3.10a | Increase patrols along the Kern River to educate anglers, and enforce angling regulations. (All segments). | annual | CDFW | ongoing
GOAL 4. RAISE PUBLIC AWARENESS ON THE UNIQUENESS OF THE NATIVE GOLDEN TROUT COMPLEX OF FISHES AND THE KERN RIVER WATERSHED.
Objective 4.1. Implement public outreach and education programs
2 | 4.1a | Construct and maintain interpretive centers at Kern River Planting Base and other locations to educate the public as to the value of native aquatic species and habitats. (Segments 1, 3 and 4). | annually | CDFW | unknown | unknown | unfunded | $ | $ | $ | $ | $ | $
3 | 4.1b | Produce brochures explaining Kern River rainbow trout planting program (distribute via census takers & at visitor centers). (Segments 1, 2 and 4). | 1 | CDFW | 2016 | CDFW |  |  |  |  | $
3 | 4.1c | Convert all Salmonids in the Classroom eggs allotted to the Kern River Valley schools to KRRT. | annually | CDFW | 2016 | CDFW |  |  |  |  | $
3 | 4.1d | Add information about KRRT program on agency web sites as possible and practical. (All segments). | 1 | CDFW, SEKI, INF, SNF | 2015 | CDFW, SEKI, INF, SNF |  |  |  | $
4 | 4.1e | Construct permanent streamside trout egg incubator at youth camps at Freeman and Dry Meadow Creeks. | 1 | CDFW/ stakeholders | 2018 | CDFW, KRTF | unfunded | [5 empty] | $
Objective 4.2. Implement Strategic Program Management
2 | 4.2a | Conduct annual coordination meetings among the State, Federal and stakeholders. | annually | CDFW | scheduled
2 | 4.2b | Brief annual presentation and summary report at spring Upper Kern Fish Enhancement Fund Meeting. | 1 | CDFW | scheduled
4 | 4.2c | Produce 5-yr progress reports of expenditures, major findings, and accomplishments. | 1 | CDFW | scheduled
FUNDING
HIFF =- Hatchery and Inland Fishery Fund
KRTF = Kern River Trust Fund
Note on C21: Stan Stephens: